## Slide 1: Roadmap 2024

## Slide 2: Longlist from deaneries – potential projects
Deanery | Revitalise | Renew
Bishop’s Waltham | Meon Valley Parishes Deanery wide – Children/youth/schools | Boorley Green
Fareham | Deanery wide – Children/youth/schools Holy Trinity Fareham – Choir Church | St Peter & St Paul, Fareham Welborne
Gosport | Lee-on-Solent – children & youth Alverstoke – Children & youth Haven Church (Holy Trinity) – Choir Church | 
Petersfield | Deanery wide – Children/youth/schools St Peter’s Petersfield – Choir Church | Whitehill
Deanery | Revitalise | Renew
Havant | Leigh Park -school St Mary Hayling Island – Choir Church St Faith’s Havant – Choir Church St James Emsworth – Choir Church | Berewood Horndean
Portsmouth | Paulsgrove Wymering & Cosham Southsea – children & youth St Mary’s Portsea – Choir Church St Michael Paulsgrove – Choir Church | Hilsea Eastney Harbour – Copnor & City
IOW | Sandown – The Bay School Bembridge – school Gurnard,Northwood & Cowes St John’s Newport – Choir Church St Mary’s Carisbrooke – Choir Church St John’s Ryde – Choir Church Arreton – Choir Church Bembridge – Choir Church St Mary’s Cowes – Choir Church | Newport plant from Ryde (as per strategic plan for IOW)

## Slide 3: Next steps
Long list
BST/BC
Evaluate &
prioritise
Feasibility
Impact
£ Cost
Short list
Add detail
Missional design
Impact- targets
£ Firm budget
SMMI bid
Update Draft Vision & Strategy
Create supporting SMMI bid

## Slide 4: Timing
When | What | Governance
Mar/Apr | Prioritisation & review | BST & Bishop's Council
June | Agree vision & strategy. Key points of SMMI bid | Diocesan Synod
mid-Aug | Submit SMMI bid for external review | BST & Bishop's Council/delegation
mid-Sep | Submit final bid | BST & Bishop's Council/delegation
31-Oct | Decision on SMMI bid | SMMI Board